## Issues Report
Warehouse-First Platform – Issues Report & Resolution Plan
بيان شامل بالمشكلات المكتشفة في warehouse_platform_backlog_v3.xlsx — مع تصنيفها وخطة المعالجة
ملخص تنفيذي
إجمالي المشكلات | 🔴 Critical | 🟠 High | 🟡 Medium | 🟢 Low | Open | Resolved
-934 | 0 | 0 | 0 | 0 | 28 | 0
Issue ID | Category | Severity | Issue Title | Detail | Impact | Fix Effort | Fix Suggestion | Owner | Status
بنية الملف (Excel Structure)
A-01 | بنية الملف (Excel Structure) | 🔴 Critical | لا توجد معادلات (No Formulas) | كل الأرقام مكتوبة يدويًا: عدد الـ 146 story، الملخصات، وكل إحصائية أخرى. | أي تعديل لاحق يخلق drift بين الواقع والأرقام الظاهرة في العناوين. | متوسط | تحويل جميع العناوين والملخصات إلى معادلات COUNTA/COUNTIF تشير إلى بيانات Backlog مباشرةً. | — | Open
A-02 | بنية الملف (Excel Structure) | 🔴 Critical | لا توجد Data Validation | أعمدة Issue Type, Delivery Type, Priority, Estimate ليس عليها قوائم منسدلة أو قيود إدخال. | أي شخص يستطيع كتابة قيمة خاطئة بحرية كاملة؛ يضعف موثوقية الفرز والتصفية. | متوسط | إضافة Data Validation بقوائم منسدلة (Lists) لكل عمود حرج، مع رسالة خطأ واضحة. | — | Open
A-03 | بنية الملف (Excel Structure) | 🟠 High | لا توجد Excel Tables | Backlog مجرد نطاق خلايا منسق يدويًا، وليس Table رسمية. | يضعف الفرز، التصفية، التوسعة التلقائية، والتعامل مع الملف كأداة تشغيل. | سريع | تحويل نطاق Backlog إلى Table رسمية (Insert → Table) مع اسم منطقي مثل tblBacklog. | — | Open
A-04 | بنية الملف (Excel Structure) | 🟠 High | لا توجد Auto Filter | لا يوجد فلتر في أي شيت، بما في ذلك Backlog الرئيسي. | يجعل التصفية اليومية بطيئة ومؤلمة للمستخدم. | سريع | تفعيل Auto Filter على صف Header في Backlog وOverview على الأقل. | — | Open
A-05 | بنية الملف (Excel Structure) | 🟠 High | لا توجد Conditional Formatting | الألوان الحالية ثابتة يدويًا فقط وليست ناتجة عن قواعد ديناميكية. | أي تعديل للقيم لن يغير الألوان تلقائيًا، فيبقى اللون الخاطئ ظاهرًا. | متوسط | إضافة قواعد Conditional Formatting لـ Priority (P0=أحمر، P1=برتقالي، P2=أصفر) وEstimate. | — | Open
A-06 | بنية الملف (Excel Structure) | 🟡 Medium | لا توجد Sheet Protection | كل الشيتات قابلة للتعديل الكامل بدون أي حماية. | خطر تعديل عرضي للهيكل أو العناوين أو القيم المرجعية في ملف مرجع رسمي. | سريع | حماية شيتات Read Me وOverview وKey Decisions من التعديل، مع السماح للـ Backlog. | — | Open
A-07 | بنية الملف (Excel Structure) | 🟡 Medium | لا توجد Defined Names | لا توجد Named Ranges أو Defined Names داخل الـ Workbook. | يصعّب كتابة معادلات قابلة للقراءة ويؤكد الطابع اليدوي للملف. | متوسط | تعريف Names للنطاقات الرئيسية مثل Backlog_Priority وBacklog_Estimate وBacklog_Epic. | — | Open
A-08 | بنية الملف (Excel Structure) | 🟢 Low | خصائص Metadata شبه فارغة | creator=openpyxl, title=None, subject=None, description=None, keywords=None, revision=0. | يضعف traceability والاعتماد الرسمي للملف في بيئة مؤسسية. | سريع | تحديث خصائص الملف: Title, Subject, Author, Keywords, Description. | — | Open
A-09 | بنية الملف (Excel Structure) | 🟢 Low | لا توجد إعدادات طباعة (Print Setup) | لا توجد Print Titles، لا Print Area، ولا إعدادات Page Layout. | عند طباعة الملف أو تصديره PDF تخرج الصفحات بدون headers وبتنسيق غير مقبول. | سريع | تحديد Print Area وإضافة Print Titles (صفوف العناوين) في Backlog وOverview. | — | Open
A-10 | بنية الملف (Excel Structure) | 🟢 Low | لا توجد Hyperlinks أو Comments توضيحية | لا توجد روابط داخلية أو تعليقات على خلايا حساسة أو مفاهيم تحتاج توضيحًا. | يجبر القارئ على البحث خارج الملف عن السياق. | متوسط | إضافة Comments على Acceptance Criteria المعقدة وروابط بين Overview وأول صف كل Epic. | — | Open
جاهزية Jira
B-01 | جاهزية Jira | 🟠 High | الصف الأول ليس Header (Jira CSV Issue) | الصف 1 في Backlog عنوان مدموج (A1:K1)، والـ Header الحقيقي في الصف 2. | أي استيراد مباشر لـ Jira أو أداة مماثلة ستفشل أو تستورد البيانات بشكل خاطئ. | سريع | فصل عنوان الشيت عن صف الـ Headers أو توفير نسخة Export-Ready مخصصة للاستيراد. | — | Open
B-02 | جاهزية Jira | 🟡 Medium | عنوان 'Full Jira-Ready' غير دقيق تقنيًا | العنوان يقول Full Jira-Ready Backlog لكن الملف يفتقد: header في أول صف، validations، normalized deps، tables. | يخلق توقعات خاطئة عند الاستخدام الفعلي. | سريع | تغيير العنوان إلى 'Structured Backlog — Requires Export Processing for Jira Import'. | — | Open
B-03 | جاهزية Jira | 🟡 Medium | Priority وDelivery Type يكرران بعضهما | المصفوفة: P0/P1=MVP، P2=Nice-to-have. أي أن Priority لا يضيف بُعدًا مستقلًا. | يضاعف البيانات بدون قيمة تحليلية إضافية حقيقية. | متوسط | إما إزالة أحد العمودين أو إعادة تعريف معيار Priority بشكل مستقل عن Delivery Type. | — | Open
الاعتماديات (Dependencies)
C-01 | الاعتماديات (Dependencies) | 🔴 Critical | دوائر اعتماد (Circular Dependencies) | E03-009 يعتمد على Epic 4 بينما Epic 4 يعتمد على Epic 3. E05-002/E05-004 يعتمدان على Epic 11 بينما Epic 11 يعتمد على Epic 5. E07-008 يعتمد على Epic 10 بينما Epic 10 يعتمد على Epic 7. | تخلق deadlock منطقي في التخطيط التنفيذي وتمنع بناء خطة تسليم خطية. | عالي | مراجعة وفك كل دائرة اعتماد: تحديد أي dependency هو partial/optional وتوثيقه صراحةً. | — | Open
C-02 | الاعتماديات (Dependencies) | 🟠 High | Dependencies على Epics لاحقة بدون توضيح | مثال: E02-011 يعتمد على Epic 3، E04-013 يعتمد على Epic 10، E03-012 يعتمد على Epic 7. | يبدو كتضارب في التسلسل ويصعّب على الفريق فهم خطة التنفيذ. | متوسط | إضافة عمود 'Dependency Type' بقيم: Blocks / Partial / Optional / External. | — | Open
C-03 | الاعتماديات (Dependencies) | 🟠 High | عمود Dependencies غير موحد (97 صيغة مختلفة) | يحتوي على: Story IDs، أسماء Epics، مفاهيم عامة، مراجع جزئية، عبارات بشرية. | غير صالح كاعتمادية قابلة للإدارة أو كمدخل منظم لـ Jira. | عالي | توحيد الصيغة: استخدام Story IDs فقط (E01-001) مع فصل بفاصلة. نقل الشرح إلى عمود Notes. | — | Open
C-04 | الاعتماديات (Dependencies) | 🟠 High | Dependencies غامضة وغير قابلة للتتبع | مثال: 'All above', 'Epic 2 MVP', 'Count workflow', 'Daily count workflow', 'Epic 10 partial'. | لا يمكن تتبعها أو تحويلها لـ Jira links، تصبح dead weight أثناء التنفيذ. | متوسط | استبدال كل عبارة غامضة بـ Story ID محدد أو حذفها والإشارة إلى Epic في عمود Notes. | — | Open
الأولويات والتقديرات
D-01 | الأولويات والتقديرات | 🟠 High | P0 متضخمة (61% من الـ Backlog) | التوزيع الفعلي: P0=89 (61%)، P1=16 (11%)، P2=41 (28%). | P0 تفقد معناها كـ blocker حقيقي عندما تشمل أكثر من نصف المشروع. | عالي | إعادة تعريف P0 كـ 'blocker for MVP go-live' فقط. الهدف: P0 ≤ 30% من الـ Backlog. | — | Open
D-02 | الأولويات والتقديرات | 🟠 High | P0 متضخمة في Epics محددة | Epic 3: 9/12 بـ P0 (75%). Epic 4: 10/13 (77%). Epic 9: 8/11 (73%). | يؤكد أن معيار الـ blocker لم يُشدّ كفاية في هذه المناطق. | عالي | مراجعة كل P0 في هذه الـ Epics: ما الذي يحدث حرفيًا لو أُجّل؟ فقط الإجابة 'MVP يتوقف' تبرر P0. | — | Open
D-03 | الأولويات والتقديرات | 🟡 Medium | XS غير مستخدم رغم تعريفه في Read Me | التوزيع: XS=0، S=29، M=86 (59%)، L=27، XL=4. | نظام التقدير غير مستخدم بكامل دقته، وبعض المهام الصغيرة قد تكون مندمجة في M. | متوسط | مراجعة M stories: أي منها يمكن كسره لـ S أو XS؟ XS = أقل من 3 ساعات تنفيذ. | — | Open
D-04 | الأولويات والتقديرات | 🟡 Medium | Timeframes لا تتطابق مع مجموع التقديرات | مثال: Epic 1 مكتوب 6–8 أسابيع، لكن حساب التقديرات يعطي ≥18 أسبوع لمطور واحد. Epic 4: مكتوب 5–6 مقابل ≥14.8 أسبوع. | يسبب سوء فهم إداري خطير إذا قُرئت الـ Timeframes على أنها خطة خطية. | عالي | إضافة ملاحظة صريحة في Overview: 'Timeframes تفترض فريقًا متوازيًا من N أشخاص'. | — | Open
الاتساق والجودة
E-01 | الاتساق والجودة | 🟡 Medium | عدم اتساق أسماء Epics بين الشيتات | مثال: 'Deployment & Core Foundation' (Overview) مقابل 'E1: Core Foundation' (Backlog). 'Advanced Counting' مقابل 'E4: Adv. Counting'. 'Warehouse Workspace' مقابل 'E8: WH Workspace'. | يربك أي mapping أو reporting أو script يعتمد على اسم الـ Epic. | متوسط | توحيد أسماء الـ Epics بصيغة واحدة في كل الشيتات: 'E1: Core Foundation' مثلاً. | — | Open
E-02 | الاتساق والجودة | 🟡 Medium | قواعد Read Me غير Enforced داخل الملف | الأولويات، التقديرات، Issue Type، Delivery Type كلها موثقة في Read Me لكن غير مقيدة فعليًا. | القواعد المكتوبة فقط لا تحمي من الأخطاء البشرية. | متوسط | ربط كل قاعدة في Read Me بـ Data Validation مقابلة داخل Backlog. | — | Open
E-03 | الاتساق والجودة | 🟢 Low | تكرار نصي في Acceptance Criteria | الجملة 'Table exists with correct schema and indexes.' موجودة مرتين في الملف. | يدل على أن بعض Acceptance Criteria generic أكثر من اللازم. | منخفض | مراجعة وتخصيص Acceptance Criteria المكررة لكل Story بدلاً من نسخها حرفيًا. | — | Open
E-04 | الاتساق والجودة | 🟢 Low | مسافة مزدوجة في عنوان Backlog | النص الحالي: 'Full Jira-Ready Backlog (146 stories)' — مسافتان قبل القوس. | خطأ شكلي يقلل الاحترافية في ملف مرجعي رسمي. | سريع | تصحيح المسافة لتصبح مسافة واحدة فقط. | — | Open
E-05 | الاتساق والجودة | 🟢 Low | Unicode/Emoji داخل Read Me | الـ Emoji المستخدمة: 📐 🎯 📦 🚚 🏗 داخل نصوص Read Me. | قد يسبب تفاوت عرض أو مشاكل توافق في بعض بيئات Windows القديمة أو عند الطباعة. | منخفض | استبدال Emoji بنص Unicode آمن أو رموز ASCII بسيطة (→ • ★) للتوافق الكامل. | — | Open
E-06 | الاتساق والجودة | 🟢 Low | الشيت النشط عند الفتح هو Read Me وليس Backlog | الملف يفتح على Read Me كشيت افتراضي. | ليس مثاليًا إذا كان الملف يُستخدم يوميًا كأداة تشغيل — يضيف click إضافية غير ضرورية. | سريع | تغيير الشيت الافتراضي عند الفتح إلى Backlog أو Overview. | — | Open
E-07 | الاتساق والجودة | 🟢 Low | Summaries مكتوبة يدويًا وغير مشتقة من البيانات | كل الإحصائيات في العناوين مكتوبة manually وليست معادلات. | أي تعديل للبيانات لن يحدّث الـ Summaries تلقائيًا — يخلق technical debt. | متوسط | استبدال كل رقم في العناوين بمعادلات COUNTA/COUNTIF تحسب من Backlog مباشرةً. | — | Open
ملاحظة: هذا البيان يُعبّر عن الحالة الراهنة للملف فقط. يجب تحديث عمود Status لكل مشكلة بعد حلها.

## Read Me
Warehouse-First Platform – Backlog Reference Guide
📐 Estimate (Story Size)
XS | < 2 days | Quick fix, config change, small addition
S | 2–3 days | Focused feature, single screen or endpoint
M | 1 week | Multi-step feature with backend + frontend work
L | 2 weeks | Complex workflow or module with multiple moving parts
XL | > 2 weeks | Large scope — consider splitting before sprint
🎯 Priority
P0 | Epic blocker | Its absence prevents the Epic from closing or breaks a downstream foundation
P1 | Important | Needed within the Epic but can be deferred to a later sprint inside it
P2 | Nice-to-have | Enhancement or extension — not required for first close
📦 Issue Type
Story | Business-facing outcome | User-visible feature, screen, workflow, or API behaviour
Task | Technical / internal | Migration, service layer, infra, middleware, test harness
🚚 Delivery Type
MVP | Required for Epic close | Must be done before Epic is considered Done
Nice-to-have | Optional enhancement | Valuable but skippable for the first close
🏗️ Epic Execution Order
1 | Deployment & Core Foundation | Most critical — do not skip or rush
2 | Master Data Expansion
3 | Inventory Ledger Engine | Core of everything
4 | Advanced Counting | Must precede Replenishment
5 | Replenishment Workflows
6 | Transfers
7 | Procurement
8 | Warehouse Workspace
9 | Branch Workspace
10 | Reporting
11 | Reorder Recommendation Engine | Not advanced forecasting
12 | Sales Linkage | Supporting data only — not POS
13 | SaaS Readiness | Groundwork from Epic 1, full enforcement here

## Key Decisions
Warehouse-First Platform – Horizontal Architectural Decisions
Decision Area | What We Agreed | Notes
System Vision | Warehouse-first platform. Sales are secondary – used only to support replenishment decisions and reporting. | Not a POS. Not a full ERP.
Build Strategy | Extend the existing codebase. No rewrite from scratch. | Leverage existing auth, items, branches, orders foundation.
API Versioning | All new or refactored endpoints under /api/v1 | Do not break existing endpoints in one shot.
Tenant ID | tenant_id enters from Epic 1 on all new/core tables. Migration plan for existing tables. | Designed tenant-aware from day one, not retrofitted later.
Offline Strategy | Offline-tolerant (NOT offline-first) for branch-critical screens only. | local draft persistence + retry queue + sync indicators + idempotent submit
No Service Worker | No full service worker offline app now. Revisit only if field ops require long disconnected periods. | Current risk: temporary disconnects, weak signal, accidental double submit.
Idempotency Contract | Every critical mutation supports client_request_id. Unique key = (tenant_id, client_request_id, operation_name) response_reference only (not snapshot) expires_at = 48h | request_hash is optional for debugging only.
Idempotency Cleanup | Scheduled cleanup job deletes records past expires_at. Indexes: client_request_id, expires_at, tenant_id | Prevents table bloat in production.
Forecasting Scope | Start with Reorder Recommendation Engine (min/max, reorder point, avg consumption, lead time, safety stock). NO advanced ML forecasting in early phases. | Forecasting intelligence only after stable history data exists.
Sales Scope | Daily summaries, manual import, basic APIs only. No cashier, no POS, no split bills, no refund engine. | Sales used as input signal for replenishment and reporting.
Deployment Target | Application will be deployed on a server. Build as a deployable product from day one. | No localhost hardcoding. Env-based config. Production-safe from Epic 1.
Environment Strategy | Separate configs: .env.local / .env.staging / .env.production No secrets in code.
Database Strategy | PostgreSQL for production. All changes via clean migrations. No schema drift. | SQLite acceptable for local dev only.
Frontend Build | Production uses vite build + static serving (nginx). NOT Vite dev server. | Base URL from env variable.
Logging | Structured server-suitable logging from Epic 1. Not just console prints. | Enables monitoring and traceability on server.
Backup Ownership Rule | Backup is NOT complete unless: - Backup Owner named - Restore Owner named - Verification Owner named - Alert channel for backup failure defined - Results documentation location defined | A backup with no owner = no backup.
Go-Live Gate | No first production deployment without passing Backup & Recovery Checklist: - Backup mechanism defined - Offsite/separate storage confirmed - Backup frequency set - Retention period set - Restore tested at least once - Recovery steps documented - Seed data separated from production data - Rollback plan exists | This is a hard gate, not a suggestion.
Testing Priority | Integration tests > unit tests alone. Layers: unit → integration → API → workflow → seeded demo validation
Definition of Done (Project) | Every stock number traceable to a ledger entry Every workflow has a clear status model Every critical operation has an audit log Duplicate submit never executes twice Branch screens tolerate weak connectivity All new endpoints under /api/v1 Core tables are tenant-aware App runs on local + staging + production Frontend builds as production artifact Backend has health checks

## Overview
Warehouse-First Platform – Epic Overview
# | Epic Name | Goal | MVP Scope | Nice-to-have | Dependencies | Risks | Definition of Done | Testing Scope | Timeframe (weeks)
1 | Deployment & Core Foundation | Stabilize the codebase and make it deployment-ready. This is the most critical Epic. | • Service layer extraction • Unified permissions + object-level auth • Standard error model • audit_logs activation • /api/v1 prefix • tenant_id strategy • idempotency_requests table + middleware • Env separation (local/staging/prod) • Health check endpoint • Server-suitable logging • Migrations discipline • Integration test harness | • Structured JSON logging • Request correlation IDs • Release metadata endpoint • Shared response envelope | None – this is the foundation | • Scope creep in refactoring • Breaking existing endpoints • Underestimating time needed | • Core services work via service layer • Permissions unified and tested • Idempotency live (backend + API) • Audit logs active • Config is production-ready • Health endpoint exists • Migrations stable • Basic integration tests pass | • Unit tests (services) • Integration tests (inventory/orders/dashboard) • Duplicate request tests • Auth tests • Env/config tests • Migration smoke tests | 6–8
2 | Master Data Expansion | Upgrade item master data to support real warehouse operations. | • item_type, storage_type • purchase_unit, supply_unit, conversion_ratio • preferred_supplier_id • lead_time_days, shelf_life_days • reorder_point, safety_stock • Multi-unit conversion support • Substitute items (basic) • Updated item screens + APIs | • ABC classification • Assortment rules per branch • Branch-specific stock policies • Bulk item import | Epic 1 | • Over-engineering data model • Unit logic conflicting with stock logic • Breaking existing item records | • One item can be defined for purchase, storage, and distribution • Unit conversions are correct and tested • New fields reflected in UI, API, and DB • Migration is clean and safe | • Unit conversion tests • CRUD API tests • Integration tests (item/unit/supplier) | 4–5
3 | Inventory Ledger Engine | Make the ledger the single source of truth for every stock movement. | • Unified stock_transactions ledger • Per-movement: source, destination, qty, reference, reason, user, timestamp, before/after balance • Stock card API • Movement history screen • Ledger posting from: receipt, dispatch, receiving, adjustment, reconciliation | • Reservation hooks • Valuation hooks • Document abstraction layer | Epic 1, Epic 2 (partial) | • Balance calculation errors • Duplicate movements • Poor indexing causing slow queries at scale | • No stock change happens outside ledger • Any stock number traceable to its source movement • Stock card is accurate • Performance acceptable on staging | • Balance mutation tests • Duplicate post prevention • End-to-end movement tests • Index/query performance checks | 6–8
4 | Advanced Counting | Transform inventory counting into a professional workflow with approval and reconciliation. | • count_sessions + count_session_lines tables • Daily branch count • Recount workflow • Variance reason enforcement • Approval flow • Reconciliation posting to ledger • Count list, entry, variance, approval screens | • Blind count • Cycle count scheduling • Surprise audit • Compliance scoring | Epic 3 | • Conflicts between count and reconciliation • Poor UX in entry screens • Double-submit from branches | • Count can be opened, submitted, recounted, approved, reconciled • Variance reasons enforced where required • Reconciliation updates ledger correctly • Draft not lost on connectivity issues | • Full count workflow tests • Reconciliation integration tests • Permission tests • Draft/retry behavior tests | 5–6
5 | Replenishment Workflows | Expand existing orders into a full branch supply workflow. | • Manual, scheduled, auto replenishment types • Suggested quantity source • Branch + warehouse review • Partial approval • Picking → dispatch → receiving states • Discrepancy handling | • Route grouping • Branch priority rules • Delivery windows | Epic 3, Epic 4 | • Status model bloat • Logic duplication across request/dispatch/receiving | • Order moves end-to-end without logic gaps • Partial approval and discrepancies supported • Idempotent submit on critical actions | • End-to-end workflow tests • Authorization tests • Duplicate submit tests | 6–8
6 | Transfers | Build a standalone module for inter-location stock transfers. | • Warehouse-to-warehouse, warehouse-to-branch, branch return • Statuses: draft → approved → dispatched → received → cancelled • Transfer lines + history | • Emergency transfer • Partial receive • Advanced discrepancy handling | Epic 3, Epic 5 (partial) | • Logic overlap with replenishment • Complex multi-location balance tracking | • Every transfer has a clear lifecycle • Balances move accurately • Ledger entries are correct | • Transfer posting tests • Dispatch/receive integration tests • Status transition tests | 4–5
7 | Procurement | Add a complete purchase cycle from supplier to stock. | • Suppliers + supplier-item mapping • Purchase orders + PO lines • Partial receiving • Rejection reasons • Supplier returns • Basic supplier performance metrics | • Landed cost • Invoice matching • Contract pricing • Advanced supplier scorecards | Epic 2, Epic 3 | • Scope bleed from replenishment • Stock posting errors on partial receive | • PO lifecycle works end-to-end • Receipts update stock and ledger correctly • Suppliers linked to items | • PO workflow tests • Stock receipt integration tests • Supplier CRUD tests | 6–7
8 | Warehouse Workspace | Provide a real daily-operations UI for warehouse staff. | • Warehouse dashboard • Receiving queue • Picking queue • Dispatch queue • Transfer queue • Count queue | • Low stock alerts widget • Pending actions widget • Operator-specific filters • Workload balancing | Epics 3, 5, 6, 7 | • UI overcrowding • Dev-server assumptions leaking to production build | • Warehouse user can complete daily tasks from one workspace • Lists reflect real system states • UI works as production build | • UI flow tests • Role-based navigation tests • API integration tests | 4–5
9 | Branch Workspace | Provide a lightweight, connectivity-tolerant UI for branch operations. | • Branch stock view, daily count, request, receiving, exception request screens • Local draft persistence • Retry queue • Sync status indicators • Double-submit protection | • Guided workflows • Richer branch dashboard • Assisted receiving UX | Epics 4, 5, Epic 1 (offline approach) | • Weak network losing data • Inconsistent offline handling across screens | • Input is never lost • Submit never executes twice • Sync state is always visible • Retry behavior is predictable | • Offline-tolerant UI tests • Retry tests • Idempotent API tests • Branch workflow end-to-end tests | 5–6
10 | Reporting | Build operational and management reports from the trusted ledger. | • Stock on hand, low stock, branch variance • Warehouse fulfillment rate • Report service layer | • Stock valuation, overstock, dead stock • Supplier fill rate, order turnaround • Count compliance • Executive scorecards • Scheduled reports • Export center | Epics 3, 4, 5, 7 | • Reports on unstable data • Calculation logic scattered in endpoints | • Every report has a clear data source • Calculations are traceable • Acceptable performance on deployment environment | • Report calculation tests • Seeded data validation • Access control tests • Performance smoke tests | 5–6
11 | Reorder Recommendation Engine | Build a simple, explainable reorder recommendation engine (NOT advanced forecasting). | • Min/max logic • Reorder point calculation • Recent average consumption • Lead time awareness • Safety stock consideration • Branch replenishment suggestions | • Weighted averages • Branch class adjustments • Event uplift • Purchase suggestion list • Seasonality (later) | Epics 2, 3, 5, 10 | • Poor data quality undermining recommendations • Premature advanced forecasting | • Recommendations are explainable (inputs visible) • Outputs can be converted to actual orders • Not a black box | • Recommendation logic tests • Scenario tests • Seeded data verification | 4–5
12 | Sales Linkage | Connect sales as a supporting data input only – not a core workflow. | • Daily sales summaries by branch • Sales by item/category • Manual CSV import • Sales feed APIs | • Basic consumption linkage • External POS adapters • Scheduled imports • Anomaly detection | Epic 10, Epic 11 (partial) | • Unintended scope creep toward POS • Inconsistent data from external sources | • Sales data feeds reports and recommendations • Module does NOT become cashier/POS scope | • Import validation tests • Aggregation tests • Reporting impact tests | 3–4
13 | SaaS Readiness | Prepare the platform to serve multiple clients without painful restructuring. | • tenant_id on all core business tables • Tenant-scoped auth • Tenant-aware queries • Tenant settings • Tenant seed strategy • Tenant-safe audit + idempotency | • Feature flags • Subscription plan skeleton • Tenant admin panel • Branding controls | All previous Epics. tenant_id groundwork starts in Epic 1. | • Migration pain if delayed • Cross-tenant data leaks if enforcement is weak | • No cross-tenant leakage possible • Core tables are tenant-aware • Tests cover tenant isolation | • Tenant isolation tests • Migration verification tests • API scope tests | 6–8 (incremental)

## Backlog
Warehouse-First Platform – Full Jira-Ready Backlog (146 stories)
Story ID | Epic | Issue Type | Delivery Type | Story Title | Description | Priority | Estimate | Dependencies | Acceptance Criteria | Notes
E01-001 | E1: Core Foundation | Task | MVP | Extract service layer from routers | Move all heavy business logic out of FastAPI routers into dedicated service classes. Routers become thin controllers only. | P0 | L | — | All core business operations execute through a service layer. Routers contain no business logic. | Start here before any other Epic 1 task.
E01-002 | E1: Core Foundation | Task | MVP | Centralize permission checks | Create a unified authorization layer. Replace scattered permission logic with a single source of truth. | P0 | M | Service layer | Permission checks are not duplicated. A single change point controls access rules.
E01-003 | E1: Core Foundation | Task | MVP | Complete object-level authorization | Every API call verifies not just role, but that the user has rights to the specific object being accessed. | P0 | M | Centralize permissions | No user can access objects outside their authorized scope. Integration tests cover edge cases.
E01-004 | E1: Core Foundation | Task | MVP | Implement standard error model | Define a unified error response schema: {error_code, message, detail}. Eliminate ad-hoc error shapes. | P1 | S | — | Every error response follows the same structure.
E01-005 | E1: Core Foundation | Task | MVP | Activate audit logs for critical operations | Enable audit_log entries for all write operations: create, update, approve, reject, dispatch, receive, adjust. | P0 | M | Service layer | Every critical mutation has an audit trail with user, timestamp, before/after state.
E01-006 | E1: Core Foundation | Task | MVP | Enforce /api/v1 prefix on all new endpoints | All new routes and any refactored routes use /api/v1/... prefix. | P0 | S | — | New endpoints are versioned. No breaking changes to old endpoints.
E01-007 | E1: Core Foundation | Task | MVP | Add tenant_id to new core tables + migration plan | Add tenant_id to all newly created tables. Document migration plan for existing tables. | P0 | L | — | New tables include tenant_id. Migration plan reviewed before execution. | Critical: enables SaaS without painful retrofit.
E01-008 | E1: Core Foundation | Task | MVP | Create idempotency_requests table | Table: id, tenant_id, client_request_id, operation_name, user_id, status, response_reference_type, response_reference_id, request_hash (nullable), created_at, expires_at. Indexes on (tenant_id, client_request_id, operation_name) and expires_at. | P0 | M | tenant_id strategy | Table exists with correct schema and indexes. | Unique key = (tenant_id + client_request_id + operation_name)
E01-009 | E1: Core Foundation | Task | MVP | Build idempotency middleware/service | Intercept critical mutations. Return stored result on duplicate. Execute and store on first call. | P0 | L | Idempotency table | Duplicate submit of any critical mutation returns same result without re-executing. Integration test confirms this. | Applies to: submit inventory, approve/reject, dispatch, receive, PO receipt, stock adjustment, count submission.
E01-010 | E1: Core Foundation | Task | MVP | Build cleanup job for idempotency records | Scheduled job deletes idempotency_requests where expires_at < now(). Default window: 48h. | P1 | S | Idempotency table | Old records are purged automatically. Table does not grow unbounded.
E01-011 | E1: Core Foundation | Task | MVP | Environment separation (local/staging/production) | Create .env.local, .env.staging, .env.production. Move all environment-specific values out of code. | P0 | M | — | Application runs correctly in all three environments with only env file swap. | No hardcoded localhost, no hardcoded credentials.
E01-012 | E1: Core Foundation | Task | MVP | Remove all hardcoded localhost assumptions | Audit entire codebase for hardcoded localhost URLs, fixed ports, or local-path assumptions. Replace all with env-based config. | P0 | S | Env separation | No reference to localhost or fixed paths in application code.
E01-013 | E1: Core Foundation | Story | MVP | Add health check endpoint | Implement GET /api/v1/health returning system status: DB connectivity, app version, uptime. | P1 | S | — | Health endpoint returns 200 with status payload. Suitable for monitoring and load balancer.
E01-014 | E1: Core Foundation | Task | MVP | Server-suitable backend logging | Replace console prints with structured logging. Log levels: DEBUG/INFO/WARN/ERROR. Logs include timestamp, request ID, user, operation. | P0 | M | — | Logs are readable and useful on a remote server. No sensitive data in logs.
E01-015 | E1: Core Foundation | Task | MVP | Enforce migrations discipline | All DB schema changes go through versioned migration files (Alembic). No direct schema edits. Document rollback steps. | P0 | S | — | All schema changes are in migration files. Rollback plan exists.
E01-016 | E1: Core Foundation | Task | MVP | Build integration test harness | Set up pytest with test DB, fixtures for common entities, and helpers for auth, CRUD, and workflow testing. | P0 | L | Service layer | Test suite runs cleanly. Fixtures cover: users, branches, warehouses, items, orders. | Foundation for all future Epic tests.
E01-017 | E1: Core Foundation | Task | Nice-to-have | Structured JSON logging | Emit logs as structured JSON to support log aggregation tools (ELK, Loki). | P2 | S | Server logging | Log lines are valid JSON with consistent fields.
E01-018 | E1: Core Foundation | Task | Nice-to-have | Request correlation IDs | Attach unique X-Request-ID to each request, propagate through service layer, include in logs and error responses. | P2 | S | — | Every request is traceable across logs by its correlation ID.
E01-019 | E1: Core Foundation | Task | Nice-to-have | Shared response envelope | Standardize all API responses into a common envelope: {data, meta, errors}. | P2 | M | Standard error model | API responses have consistent outer structure.
E02-001 | E2: Master Data | Task | MVP | Add item_type field to items | Add item_type enum: raw_material, packaging, consumable, finished_good. Apply clean migration. | P0 | S | Epic 1 | item_type is stored, validated, and returned via API. Migration applied cleanly.
E02-002 | E2: Master Data | Task | MVP | Add storage_type field to items | Add storage_type enum: ambient, chilled, frozen. | P1 | S | Epic 1 | storage_type is stored and returned via API.
E02-003 | E2: Master Data | Task | MVP | Add purchase_unit and supply_unit fields | Items carry separate units for procurement vs. distribution. | P0 | M | Epic 1 | purchase_unit and supply_unit are independent, validated fields linked to unit master.
E02-004 | E2: Master Data | Task | MVP | Add conversion_ratio logic | Define how purchase_unit converts to supply_unit (e.g., 1 case = 12 units). | P0 | M | purchase/supply units | Conversion produces correct results. Used in receiving, dispatch, and recommendations.
E02-005 | E2: Master Data | Task | MVP | Add preferred_supplier_id to items | Link item to a default supplier. Used in PO creation and reorder recommendations. | P1 | S | Epic 1 | preferred_supplier_id is a valid FK to suppliers table. Nullable.
E02-006 | E2: Master Data | Task | MVP | Add lead_time_days and shelf_life_days | lead_time_days = PO-to-delivery. shelf_life_days = max shelf life. | P0 | S | Epic 1 | Fields stored and validated as positive integers.
E02-007 | E2: Master Data | Task | MVP | Add reorder_point and safety_stock | Thresholds used by reorder recommendation engine. | P0 | S | lead_time_days | Fields stored and used by recommendation engine (Epic 11).
E02-008 | E2: Master Data | Task | MVP | Build unit conversion service | Centralized service handling all unit conversions throughout the system. No inline conversion calculations. | P0 | M | conversion_ratio | Any conversion request goes through this service. Logic tested in isolation.
E02-009 | E2: Master Data | Story | MVP | Support substitute item (basic) | Add substitute_item_id FK on items. When out of stock, system can suggest substitute. | P1 | S | Epic 1 | substitute_item_id stored. API exposes it. Frontend shows substitute suggestion.
E02-010 | E2: Master Data | Story | MVP | Update item screens and APIs | Extend item create/edit screens and APIs to include all new fields. | P0 | M | All above | Item API supports all new fields. Screens reflect changes. No regressions.
E02-011 | E2: Master Data | Task | Nice-to-have | ABC classification | Classify items as A/B/C by value and movement frequency. | P2 | M | Epic 3 data | ABC class calculated, stored, and refreshable per item.
E02-012 | E2: Master Data | Task | Nice-to-have | Branch-specific stock policies | Per-branch overrides for min_stock, max_stock, reorder_point. | P2 | M | Epic 2 MVP | Branch-specific policies override item-level defaults in recommendations.
E02-013 | E2: Master Data | Story | Nice-to-have | Bulk item import | CSV/Excel upload for creating or updating multiple items at once. | P2 | L | Epic 2 MVP | Import validates, reports errors by row, applies changes atomically.
E03-001 | E3: Inventory Ledger | Task | MVP | Unify all movements in stock_transactions ledger | Every stock change creates a ledger entry. No stock changes outside the ledger. | P0 | XL | Epic 1, Epic 2 | Ledger is the single source of truth. No orphaned stock changes. | Most important Epic in the product.
E03-002 | E3: Inventory Ledger | Task | MVP | Add before/after balance to every transaction | Each transaction records balance_before and balance_after for the affected SKU/location. | P0 | M | Unified ledger | Any transaction shows exactly what stock was before and after.
E03-003 | E3: Inventory Ledger | Story | MVP | Build stock card API | GET /api/v1/stock/card?item_id=&location_id= returns full movement history in reverse chronological order. | P0 | M | Ledger + balance fields | Stock card returns complete, correct movement history. Matches current balance.
E03-004 | E3: Inventory Ledger | Story | MVP | Build movement history screen | Frontend screen for stock card. Filterable by date range and transaction type. | P1 | M | Stock card API | Users can trace any stock number to its source within 3 clicks.
E03-005 | E3: Inventory Ledger | Task | MVP | Ledger posting from purchase receipt | PO receipt creates purchase_receipt ledger entry, increasing stock at receiving location. | P0 | M | Unified ledger | PO receipt creates correct ledger entry. Stock increases. Idempotency applied.
E03-006 | E3: Inventory Ledger | Task | MVP | Ledger posting from warehouse dispatch | Dispatch creates warehouse_dispatch entry, decreasing warehouse stock. | P0 | M | Unified ledger | Dispatch creates ledger entry. Warehouse stock decreases correctly.
E03-007 | E3: Inventory Ledger | Task | MVP | Ledger posting from branch receiving | Branch receipt creates branch_receipt entry, increasing branch stock. | P0 | M | Unified ledger | Branch receipt creates ledger entry. Branch stock increases correctly.
E03-008 | E3: Inventory Ledger | Task | MVP | Ledger posting from stock adjustment | Manual adjustments post to ledger with mandatory reason code. | P0 | M | Unified ledger | Adjustment creates ledger entry. Reason mandatory. Idempotency applied.
E03-009 | E3: Inventory Ledger | Task | MVP | Ledger posting from count reconciliation | Count approval auto-posts count_reconciliation entries for variance lines. | P0 | M | Epic 4 | Count approval triggers correct ledger entries automatically.
E03-010 | E3: Inventory Ledger | Task | MVP | Add critical DB indexes to ledger | Index on: (item_id, location_id, created_at), (reference_id, reference_type), (tenant_id, created_at). | P0 | M | Unified ledger | Stock card queries execute in < 500ms on 1M row dataset. | Essential for production performance.
E03-011 | E3: Inventory Ledger | Task | Nice-to-have | Reservation/soft-allocation hooks | Reserve stock against a pending order before dispatch. Prevents over-allocation. | P2 | L | Unified ledger | Reserved quantity tracked separately from available quantity.
E03-012 | E3: Inventory Ledger | Task | Nice-to-have | Valuation hooks | Attach cost price to each ledger entry for future stock valuation reports. | P2 | M | Epic 7 | Each ledger entry optionally carries unit_cost.
E04-001 | E4: Adv. Counting | Task | MVP | Create count_sessions table | Fields: id, tenant_id, location_id, location_type, count_type, status, opened_by, opened_at, closed_at, approved_by, approved_at. | P0 | S | Epic 3 | Table exists with correct schema and indexes.
E04-002 | E4: Adv. Counting | Task | MVP | Create count_session_lines table | Fields: id, session_id, item_id, unit_id, expected_qty, counted_qty, variance_qty, variance_reason, recounted_qty, status. | P0 | S | count_sessions | Table exists with correct schema.
E04-003 | E4: Adv. Counting | Story | MVP | Build daily branch count workflow | Branch can open a daily count session, enter quantities, and submit for review. | P0 | L | count_sessions + lines | Branch user can open → fill → submit a daily count. Variance calculated automatically.
E04-004 | E4: Adv. Counting | Story | MVP | Build recount workflow | Specific items can be flagged for recount without reopening the full session. | P0 | M | Daily count workflow | Individual lines can be recounted. Recount result stored alongside original.
E04-005 | E4: Adv. Counting | Task | MVP | Enforce variance reason on significant variances | Variance_reason is mandatory when counted_qty differs from expected beyond a threshold. | P0 | M | Count workflow | Submissions with significant variance and no reason are rejected.
E04-006 | E4: Adv. Counting | Story | MVP | Build count approval flow | Reviewer can review submitted counts, request recount on specific lines, or approve the full session. | P0 | M | Count workflow | Approval moves session to approved. approved_by and approved_at recorded.
E04-007 | E4: Adv. Counting | Task | MVP | Build reconciliation posting to ledger | On approval, system auto-posts count_reconciliation entries for all variance lines. | P0 | M | Epic 3 ledger, count approval | Approved count creates correct ledger entries. Stock balances update accurately.
E04-008 | E4: Adv. Counting | Story | MVP | Count list screen | Screen showing all count sessions with status, location, date, and action buttons. | P0 | M | Count workflow | Users see their sessions. HQ/warehouse users see all. Filters work.
E04-009 | E4: Adv. Counting | Story | MVP | Count entry screen (offline-tolerant) | Enters counted quantities per item. Draft auto-saved locally. Retry on reconnect. Double-submit blocked. | P0 | L | Count workflow + Epic 1 offline | Draft never lost. Submit idempotent. Sync status always visible. | Most critical offline-tolerant screen.
E04-010 | E4: Adv. Counting | Story | MVP | Variance review screen | Shows all variances for a session. Reviewer can filter, request recount, or proceed to approval. | P0 | M | Count approval | Reviewer can see, filter, and act on all variances in one screen.
E04-011 | E4: Adv. Counting | Story | Nice-to-have | Blind count support | Count session where expected quantities are hidden from counter to prevent bias. | P2 | M | Count workflow | Blind count mode hides expected_qty during entry.
E04-012 | E4: Adv. Counting | Task | Nice-to-have | Cycle count scheduling | Auto-generate count sessions for item groups on a rolling schedule. | P2 | L | Epic 2 ABC class | Count schedule creates sessions by item class or category on defined cadence.
E04-013 | E4: Adv. Counting | Story | Nice-to-have | Count compliance scoring | Score each branch/location on count compliance: on-time submissions, variance rates. | P2 | M | Epic 10 reporting | Compliance score calculated and visible in reports.
E05-001 | E5: Replenishment | Story | MVP | Support manual replenishment request | Branch can submit a manual stock request with custom quantities for any item. | P0 | M | Epic 3 | Manual request created with correct items, quantities, and status = pending_review.
E05-002 | E5: Replenishment | Story | MVP | Support scheduled replenishment | System generates replenishment requests automatically on a defined schedule per branch. | P0 | L | Epic 3, Epic 11 | Scheduled requests generated on time with suggested quantities.
E05-003 | E5: Replenishment | Story | MVP | Support auto replenishment trigger | System triggers a request when stock drops below reorder_point. | P1 | L | Epic 3, reorder_point | Auto-trigger fires when stock hits threshold. Request created without manual action.
E05-004 | E5: Replenishment | Story | MVP | Suggested quantity on request lines | Each line shows suggested_qty with source: min/max, average consumption, stock cover days. | P1 | M | Epic 11 partial | Suggested qty visible with clear source label.
E05-005 | E5: Replenishment | Story | MVP | Branch review workflow | Branch can review, edit, and confirm a suggested replenishment before submitting. | P0 | M | Request creation | Branch can edit quantities, remove lines, and submit. Idempotent submit applied.
E05-006 | E5: Replenishment | Story | MVP | Warehouse review and partial approval | Warehouse can approve, partially approve, or reject request lines. | P0 | L | Branch review | Warehouse can approve all, approve subset with modified quantities, or reject. All changes audited.
E05-007 | E5: Replenishment | Story | MVP | Picking state and queue | Approved requests enter picking state. Warehouse picker sees a picking list grouped by location. | P0 | M | Warehouse approval | Picking queue shows all approved, unfulfilled requests.
E05-008 | E5: Replenishment | Story | MVP | Dispatch state | After picking, warehouse dispatches. Posts warehouse_dispatch to ledger and notifies branch. | P0 | M | Picking state | Dispatch triggers ledger entry. Branch notified. Status = dispatched.
E05-009 | E5: Replenishment | Story | MVP | Branch receiving workflow | Branch confirms receipt. Can accept, partially accept, or flag discrepancies per line. | P0 | L | Dispatch | Branch receives, posts branch_receipt to ledger. Discrepancies recorded.
E05-010 | E5: Replenishment | Story | MVP | Discrepancy handling | When received qty differs from dispatched, discrepancy is recorded with reason. | P0 | M | Receiving | Discrepancies captured, tracked, resolved. Ledger reflects final quantity.
E05-011 | E5: Replenishment | Task | Nice-to-have | Route grouping | Group branches by delivery route for efficient dispatch batching. | P2 | M | Epic 5 MVP | Dispatch batches grouped by route. Route label visible on dispatch screen.
E05-012 | E5: Replenishment | Task | Nice-to-have | Branch priority rules | Flag high-priority branches affecting fulfillment order when stock is limited. | P2 | S | Epic 5 MVP | High-priority branches appear first in warehouse review queue.
E06-001 | E6: Transfers | Task | MVP | Create stock_transfers and transfer_lines tables | Tables: id, tenant_id, source_location, destination_location, transfer_type, status, lines (item, qty, unit), history. | P0 | M | Epic 3 | Tables created with correct schema, indexes, and FK constraints.
E06-002 | E6: Transfers | Story | MVP | Warehouse-to-warehouse transfer | Move stock between two warehouses. Posts transfer_out from source, transfer_in to destination on confirmation. | P0 | L | Transfer tables, Epic 3 | Transfer lifecycle works. Both ledger entries post correctly on receive.
E06-003 | E6: Transfers | Story | MVP | Warehouse-to-branch transfer | Direct stock movement from warehouse to branch outside replenishment workflow. | P0 | M | Transfer tables | Transfer creates correct ledger entries. Not confused with replenishment orders.
E06-004 | E6: Transfers | Story | MVP | Branch return to warehouse | Branch returns stock to warehouse. Posts branch_return and warehouse_return_in. | P0 | M | Transfer tables | Return workflow creates two ledger entries. Both balances updated correctly.
E06-005 | E6: Transfers | Task | MVP | Transfer status lifecycle | Implement: draft → approved → dispatched → received → cancelled. Each transition logged. | P0 | M | Transfer tables | Invalid transitions rejected. Full history recorded.
E06-006 | E6: Transfers | Task | MVP | Transfer history and audit trail | Every status change recorded with actor and timestamp. | P1 | S | Status lifecycle | Full audit trail available for any transfer.
E06-007 | E6: Transfers | Story | Nice-to-have | Emergency transfer | Expedited transfer bypassing normal approval, going directly to dispatched. | P2 | M | Transfer lifecycle | Emergency transfers skip approval step. Flagged clearly in history.
E06-008 | E6: Transfers | Story | Nice-to-have | Partial receive on transfers | Destination can receive a subset of transferred items. | P2 | M | Transfer lifecycle | Partial receipt recorded. Remaining items stay in transit.
E07-001 | E7: Procurement | Task | MVP | Create suppliers table | Fields: id, tenant_id, name, code, contact_name, phone, email, address, active, created_at. | P0 | S | Epic 1 | Supplier CRUD works. Tenant-scoped. Searchable.
E07-002 | E7: Procurement | Task | MVP | Create supplier_items mapping | Link items to suppliers: supplier_id, item_id, supplier_sku, unit_price, lead_time_days, is_preferred. | P0 | S | Suppliers, Epic 2 | Items linked to multiple suppliers. Preferred supplier flagged.
E07-003 | E7: Procurement | Task | MVP | Create purchase_orders and PO_lines tables | PO header: tenant_id, supplier_id, status, ordered_at, expected_delivery_date. Lines: item_id, qty, unit, unit_price. | P0 | M | supplier_items | PO can be created, edited (while draft), and submitted for approval.
E07-004 | E7: Procurement | Story | MVP | PO approval workflow | PO moves through: draft → submitted → approved → ordered → partially_received → received → cancelled. | P0 | M | PO tables | Approval workflow works. Each transition logged. Invalid transitions rejected.
E07-005 | E7: Procurement | Story | MVP | Goods receiving (partial and full) | Record received quantities per line. Partial receipt supported. Each receipt posts to ledger. | P0 | L | Epic 3 ledger, PO approval | Receiving creates purchase_receipt ledger entry. Stock increases correctly.
E07-006 | E7: Procurement | Story | MVP | Rejection reasons on receiving | Receiving user can reject items per line with a reason. | P1 | S | Goods receiving | Rejections recorded per line. Rejected stock not added to inventory.
E07-007 | E7: Procurement | Story | MVP | Supplier returns | Create a supplier return document for rejected/expired items. Posts reversal to ledger. | P1 | M | Epic 3, Goods receiving | Supplier return reduces stock. Ledger entry created. Return linked to original receipt.
E07-008 | E7: Procurement | Story | MVP | Basic supplier performance metrics | Track: fill rate, average lead time, rejection rate per supplier. | P1 | M | Epic 10 partial | Metrics calculated from transaction history. Visible on supplier profile.
E07-009 | E7: Procurement | Task | Nice-to-have | Landed cost tracking | Add landed cost to PO receipts and factor into stock valuation. | P2 | L | Epic 3 valuation hooks | Landed cost stored per receipt line. Included in valuation.
E07-010 | E7: Procurement | Story | Nice-to-have | Invoice matching | Match supplier invoice against PO and receipt to verify amounts. | P2 | L | Goods receiving | Three-way match (PO, receipt, invoice) supported. Discrepancies flagged.
E08-001 | E8: WH Workspace | Story | MVP | Warehouse main dashboard | Landing page: pending orders, open picking tasks, dispatch ready, low stock alerts, open counts. | P0 | L | Epics 3,5,6,7 | Warehouse user sees operational status at a glance. All counts are accurate.
E08-002 | E8: WH Workspace | Story | MVP | Receiving queue screen | List of dispatched orders and transfers awaiting receiving confirmation. Filterable and sortable. | P0 | M | Epic 5 dispatch, Epic 6 | Warehouse receiver sees all pending items. Can click through to process each.
E08-003 | E8: WH Workspace | Story | MVP | Picking queue screen | All approved requests needing picking, sorted by priority and grouped by storage zone. | P0 | M | Epic 5 picking state | Picker sees optimized list. Can mark items as picked.
E08-004 | E8: WH Workspace | Story | MVP | Dispatch queue screen | All picked orders ready for dispatch. Dispatcher confirms dispatch triggering ledger entry. | P0 | M | Epic 5 dispatch | Dispatcher sees pick-complete orders only. Dispatch action is idempotent.
E08-005 | E8: WH Workspace | Story | Nice-to-have | Low stock and pending action widgets | Dashboard widgets: items below reorder_point and tasks requiring action. | P2 | M | Epic 3, Epic 5 | Widgets show accurate counts. Clicking drills into the relevant list.
E08-006 | E8: WH Workspace | Story | MVP | Transfer queue screen | Open transfers (inbound/outbound) for this warehouse. Status at a glance. | P1 | M | Epic 6 | Warehouse user sees all transfer activity. Can act on pending items.
E08-007 | E8: WH Workspace | Story | MVP | Count queue screen | Open or overdue count sessions. Links to entry and approval screens. | P1 | M | Epic 4 | Count queue shows sessions by status. Overdue highlighted.
E08-008 | E8: WH Workspace | Task | Nice-to-have | Operator-specific task filters | Filter queues to show only tasks for a specific operator or zone. | P2 | M | Epic 8 MVP | Filter persists per user session.
E08-009 | E8: WH Workspace | Story | Nice-to-have | Workload balancing view | Manager view showing task distribution across warehouse operators. | P2 | L | Epic 8 MVP | Manager sees operator workload. Can reassign tasks.
E09-001 | E9: Branch Workspace | Story | MVP | Branch stock view screen | Current stock levels for all items at this branch. Color-coded for low/ok/overstock. | P0 | M | Epic 3 | Branch user sees accurate, current stock. Low stock items highlighted.
E09-002 | E9: Branch Workspace | Story | MVP | Daily count screen (offline-tolerant) | Enter daily count quantities. Draft auto-saved locally every 30s. Retry on reconnect. Double-submit blocked. | P0 | L | Epic 4, Epic 1 offline | Draft never lost. Submit idempotent. Sync state always visible. | Most critical offline-tolerant screen.
E09-003 | E9: Branch Workspace | Story | MVP | Branch request screen | Create or edit a replenishment request. Draft persisted locally. Idempotent submit. | P0 | L | Epic 5, Epic 1 offline | Request submitted once regardless of retries. Draft recoverable.
E09-004 | E9: Branch Workspace | Story | MVP | Branch receiving screen | Confirm receipt of dispatched items. Record discrepancies per line. Draft persisted. | P0 | L | Epic 5 receiving, Epic 1 offline | Receiving submitted idempotently. Discrepancies captured. Draft not lost.
E09-005 | E9: Branch Workspace | Story | Nice-to-have | Exception request screen | Branch raises ad-hoc urgent request with reason and required date. | P2 | M | Epic 5 | Exception request created with reason. Flagged as high priority in warehouse queue.
E09-006 | E9: Branch Workspace | Task | MVP | Build unified draft persistence hook/service | Shared frontend hook saving form state to localStorage on change. Restores on page load. | P0 | M | Epic 1 offline approach | All branch screens share the same draft mechanism. No per-screen duplication.
E09-007 | E9: Branch Workspace | Task | MVP | Build unified retry queue service | Shared frontend service queuing failed API calls and retrying with exponential backoff. | P0 | M | Draft persistence | Failed submissions queued. Retry happens transparently. User sees queue status.
E09-008 | E9: Branch Workspace | Task | MVP | Sync status indicator component | Reusable UI component: Saved / Syncing / Synced / Retry Failed. Used on all branch screens. | P0 | S | Draft + retry services | User always knows save/sync state. No silent failures.
E09-009 | E9: Branch Workspace | Task | MVP | Double-submit protection | Submit buttons disabled after first click until response received. Backend rejects duplicates via idempotency. | P0 | M | Idempotency contract (Epic 1) | Clicking submit multiple times never results in duplicate server operations.
E09-010 | E9: Branch Workspace | Story | Nice-to-have | Guided branch workflows | Step-by-step wizard mode for less experienced staff (count, receive, request flows). | P2 | L | Epic 9 MVP | Guided mode walks user through each step with validation.
E09-011 | E9: Branch Workspace | Story | Nice-to-have | Assisted receiving flow | System pre-flags discrepancies by comparing expected vs. actual on receive. | P2 | M | Epic 9 MVP | Discrepancies pre-flagged. User confirms or overrides.
E10-001 | E10: Reporting | Task | MVP | Report service layer | Create dedicated ReportService centralizing all report queries. No report logic in routers. | P0 | M | Epics 3,4,5,7 | All report endpoints delegate to ReportService. No duplicate aggregation logic.
E10-002 | E10: Reporting | Story | MVP | Stock on hand report | Current stock levels across all locations. Filterable by warehouse, branch, item, category. | P0 | M | Report service, Epic 3 | Report shows accurate current balances matching ledger totals.
E10-003 | E10: Reporting | Story | MVP | Low stock report | Items below reorder_point or safety_stock across all locations. Sorted by urgency. | P0 | S | Stock on hand | Report shows items needing attention. Drill-down to item detail.
E10-004 | E10: Reporting | Story | MVP | Branch variance report | Summary of count variances per branch over a date range. Variance %, trend, top items. | P0 | M | Epic 4 count sessions | Report shows branch compliance and variance trends.
E10-005 | E10: Reporting | Story | MVP | Warehouse fulfillment rate | % of replenishment request lines fulfilled fully and on time, per warehouse per period. | P0 | M | Epic 5 receiving | Report shows fulfillment rate by warehouse, period, and category.
E10-006 | E10: Reporting | Story | Nice-to-have | Basic stock valuation report | Stock on hand × unit cost per item/location. | P2 | M | Epic 7 valuation hooks | Valuation report shows total stock value by location and category.
E10-007 | E10: Reporting | Story | Nice-to-have | Overstock report | Items significantly above max_stock level. Flag for redistribution or purchase pause. | P2 | S | Stock on hand | Report shows overstocked items with excess quantity and suggested action.
E10-008 | E10: Reporting | Story | Nice-to-have | Dead stock report | Items with zero movement for a configurable period (default 90 days). | P2 | M | Epic 3 movement history | Report shows items, last movement date, and current quantity.
E10-009 | E10: Reporting | Story | Nice-to-have | Supplier fill rate | % of PO lines delivered on time and in full, per supplier per period. | P2 | M | Epic 7 receiving | Report shows supplier reliability metrics.
E10-010 | E10: Reporting | Story | Nice-to-have | Order turnaround report | Average time from request creation to delivery confirmation. | P2 | M | Epic 5 workflows | Report shows operational speed and bottlenecks.
E10-011 | E10: Reporting | Story | Nice-to-have | Count compliance report | % of branches/warehouses submitting counts on time. | P2 | M | Epic 4 | Report shows which locations are compliant and which are overdue.
E10-012 | E10: Reporting | Story | Nice-to-have | Executive scorecard dashboard | Single-page summary: stock health, fulfillment rate, supplier performance, branch compliance. | P2 | L | All reports MVP | Scorecard auto-updates. Exportable as PDF.
E10-013 | E10: Reporting | Task | Nice-to-have | Export center | Centralized export for all reports to Excel, CSV, or PDF. | P2 | M | Epic 10 MVP | Any report exportable in supported formats.
E11-001 | E11: Reorder Engine | Task | MVP | Build min/max reorder logic | If current stock < reorder_point, generate recommendation to reorder up to max_stock. | P0 | M | Epic 2, Epic 3 | Recommendations generated correctly for all items below reorder_point.
E11-002 | E11: Reorder Engine | Task | MVP | Calculate recent average consumption | Compute average daily/weekly consumption per item per location from ledger history (configurable period). | P0 | M | Epic 3 movement history | Consumption figure calculated, stored, refreshed on schedule.
E11-003 | E11: Reorder Engine | Task | MVP | Lead time awareness in recommendations | Adjust suggested order quantity to ensure stock won't run out during lead time. | P0 | M | Avg consumption, lead_time_days | Recommendations factor in lead time. Edge case: zero lead time handled.
E11-004 | E11: Reorder Engine | Task | MVP | Safety stock floor in recommendations | Recommended order includes buffer above safety_stock level, not just reorder_point. | P0 | S | Min/max logic | Safety stock floor respected in all recommendations.
E11-005 | E11: Reorder Engine | Story | MVP | Branch replenishment suggestion list | API and screen showing suggested replenishment per branch: item, current stock, suggested qty, basis. | P0 | M | All above | Branch suggestion list is readable, actionable, and explains its own logic.
E11-006 | E11: Reorder Engine | Story | Nice-to-have | Purchase suggestion list | API and screen showing suggested POs per supplier, grouped by supplier. | P2 | M | All above, Epic 7 | Purchase suggestions group by supplier. Can be converted to PO draft.
E11-007 | E11: Reorder Engine | Task | Nice-to-have | Weighted recent consumption | Give higher weight to recent periods vs. older periods in consumption calculation. | P2 | M | Avg consumption | Weighted average is more responsive to recent demand changes.
E11-008 | E11: Reorder Engine | Task | Nice-to-have | Branch class adjustments | Apply different reorder multipliers for high-volume vs. low-volume branches. | P2 | M | Epic 2 branch policies | Recommendations scaled by branch class.
E12-001 | E12: Sales Linkage | Task | MVP | Create sales_summaries table | Fields: id, tenant_id, branch_id, date, total_sales_amount, total_items_sold, source, created_at. Indexes on (branch_id, date, tenant_id). | P0 | S | Epic 1 | Table created with correct schema and indexes.
E12-002 | E12: Sales Linkage | Task | MVP | Create sales_summary_lines table | Item-level sales: summary_id, item_id, qty_sold, unit, sales_amount. | P0 | S | sales_summaries | Table created with correct FK constraints.
E12-003 | E12: Sales Linkage | Story | MVP | Manual sales entry screen | Branch or HQ enters daily sales totals manually per branch per day. | P0 | M | Sales tables | Manual entry works. Duplicate entry for same branch/date prevented.
E12-004 | E12: Sales Linkage | Story | MVP | CSV import for sales summaries | Upload CSV with daily sales data per branch/item. Validates format, reports errors by row. | P0 | M | Sales tables | Import validates, inserts clean rows, reports errors. Idempotent.
E12-005 | E12: Sales Linkage | Task | Nice-to-have | Sales feed into consumption reports | Sales data visible in Epic 10 reports as consumption signal. | P2 | M | Epic 10 report service | Sales data integrated into branch consumption analysis.
E12-006 | E12: Sales Linkage | Task | Nice-to-have | Sales data feeds recommendation engine | Epic 11 engine optionally uses sales data when ledger consumption is insufficient. | P2 | M | Epic 11 | Recommendation engine can switch between ledger-based and sales-based consumption.
E12-007 | E12: Sales Linkage | Task | Nice-to-have | External POS sync adapters | API integration to pull sales data automatically from external POS systems. | P2 | XL | Sales tables | Adapter runs on schedule. Handles failures gracefully.
E12-008 | E12: Sales Linkage | Story | Nice-to-have | Sales anomaly detection | Flag statistical outliers in daily sales for review. | P2 | M | Epic 12 MVP | Anomalies flagged in reporting. Threshold configurable.
E13-001 | E13: SaaS Readiness | Task | MVP | Apply tenant_id to all core business tables | Audit all tables. Add tenant_id where missing. Run migrations. Update all queries to filter by tenant_id. | P0 | XL | All Epics | No business table lacks tenant_id. All queries are tenant-scoped. | Groundwork from Epic 1. Full enforcement here.
E13-002 | E13: SaaS Readiness | Task | MVP | Tenant-scoped authentication | Auth tokens carry tenant context. All API requests resolve to a tenant. Cross-tenant access impossible. | P0 | L | tenant_id migration | User from Tenant A cannot access Tenant B data under any circumstances.
E13-003 | E13: SaaS Readiness | Task | MVP | Tenant-aware query enforcement | Middleware automatically appends tenant_id filter to all DB queries. | P0 | L | Tenant-scoped auth | Tenant filter applied at ORM level. Impossible to forget on a new endpoint.
E13-004 | E13: SaaS Readiness | Task | MVP | Tenant settings table | Per-tenant configuration: currency, timezone, count frequency, min/max defaults, feature toggles. | P0 | M | tenant_id migration | Settings stored and applied per tenant. New tenant gets sensible defaults.
E13-005 | E13: SaaS Readiness | Task | MVP | Tenant seed strategy | Separate seed data for local dev, demo environment, and production onboarding. | P0 | M | Tenant settings | Three seed modes exist. Production onboarding creates clean, minimal data.
E13-006 | E13: SaaS Readiness | Task | MVP | Tenant-safe audit logs | Audit logs are tenant-scoped. Tenant admin sees only their own audit trail. | P0 | S | tenant_id migration | Audit log queries always filter by tenant_id.
E13-007 | E13: SaaS Readiness | Task | MVP | Tenant-safe idempotency verification | Verify idempotency_requests enforcement is complete across all tenants. | P1 | S | Idempotency table (Epic 1) | Idempotency records cannot leak across tenants.
E13-008 | E13: SaaS Readiness | Task | Nice-to-have | Feature flags per tenant | Toggle features on/off per tenant without code deployment. | P2 | M | Tenant settings | Feature flag checked at runtime.
E13-009 | E13: SaaS Readiness | Task | Nice-to-have | Subscription plan skeleton | Define plan tiers with feature sets. Associate tenant with a plan. | P2 | L | Feature flags | Plan limits enforced at API level.
E13-010 | E13: SaaS Readiness | Story | Nice-to-have | Tenant admin panel | Dedicated UI for tenant admins to manage users, settings, and view analytics. | P2 | XL | All above | Tenant admin can manage their environment independently.